## Read Me First
Quality Gate Version date: July 11, 2025
Purpose | The purpose of this accelerator is to ensure all key areas are addressed before moving to the next project phase. All project documentation and results should be recorded, with links provided to ensure proper documentation.
SENSITIVITY NOTE: This file becomes CONFIDENTIAL when filled with Customer Data
Project Identification
Project Name |  | Project Number | Project Type
SAP S/4HANA Cloud ERP Implementation |  |  | SAP S/4HANA Cloud Public Edition
Customer Name |  |  | Customer Number | Project Start To Finish
Home Control Pte Ltd
Project Sponsor |  | Program Manager (Partner) |  | Project Manager (Customer)
|  | Alex Chua |  | Minting
Project Manager (Customer) |  | Project Manager (Partner) |  | Project Manager (Partner)
Rocky Cai |  | Jennifer |  | Chakriya
Guidelines for Completing the Assessment: 'Checklist Items'
1. Review the Quality Gate questions before moving to the next project phase. 2. Empty cells are highlighted in red and turn white once compelted, providing a quick overview of unanswered questions. 3. Engage all relevant stakeholders and ensure proper sign-offs are obtained. 4. Include links to all key documents, such as sign-off and handover documentation.

## Discover Quality Gate
CHECK ID | Title | Description | Answer | Status |  |  |  | Maintain Description Here | Copy Paste This Cell as Value to Column B
CL001 | Learn on a SAP S/4HANA Cloud Trial System | Ensures the project team/stakeholders have engaged with a trial system to explore core functionalities, user experience, and solution familiarity. | Yes | Completed | 01 | - | CL001 | Who is the lead adoption driver from the Customer side for this wave? | 01-Who is the lead adoption driver from the Customer side for this wave?
CL002 | Request Demonstration Landscape | Confirms a demo landscape is requested and available for deeper product demos with a tenant for customizing and configuration and a tenant for developer extensibility. | Yes | Completed | 02 | - | CL002 | Who is the lead adoption driver from the Partner side for this wave? | 02-Who is the lead adoption driver from the Partner side for this wave?
CL003 | Executing a SAP Digital Discovery Assessment | All key stakeholders to gain access to the Digital Discovery Assessment tool and to capture the scope by defining relevant business capabilities; identify integrations and extensibility needed in the customer’s landscape; leverage Q&A sections; capture notes; and document any additional requirements specific to the customer’s move to the SAP Business Suite. | Yes | Completed | 03 | - | CL003 | Has SAP's Cloud ERP strategy and positioning been clarified with the customer? Specific topics include: Two-tier landscape highlights, self-service engagement model, change projects, Agile methodology, upgrades, regression testing and change management. | 03-Has SAP's Cloud ERP strategy and positioning been clarified with the customer? Specific topics include: Two-tier landscape highlights, self-service engagement model, change projects, Agile methodology, upgrades, regression testing and change management.
CL004 | Generate SAP Digital Discovery Report | Generate a report from the Digital Discovery Assessment app after the customer scoping is finalized. This report serves as the foundation for determining the project scope during the various phases of implementation. | Yes | Completed | 04 | - | CL004 | Is there a defined and documented business scope outlining intended business processes for initial and subsequent waves? | 04-Is there a defined and documented business scope outlining intended business processes for initial and subsequent waves?
CL005 | Execute the Cloud Mindset | Evaluating the organization's readiness for the cloud subscription business model. The results of this assessment help raise awareness among business stakeholders about key organizational change management (OCM) topics and activities. | Yes | Completed | 05 | - | CL005 | Does the business scope documentation inlcude current IT architecture and integration needs, have all integrated applications (SAP & Non-SAP) been considered when determining the scope of the project? | 05-Does the business scope documentation inlcude current IT architecture and integration needs, have all integrated applications (SAP & Non-SAP) been considered when determining the scope of the project?
CL006 | Select the Right Cloud Partner | Find the right SAP Partner for the SAP cloud implementation. The key to a successful implementation is a partner’s understanding and embracing of SAP Activate for S/4HANA Cloud and a deep solution knowledge in SAP S/4HANA Cloud, proven through a fully certified, dedicated delivery team. | Yes | Completed | 06 | - | CL006 | Has a DDA (Digital Discovery Assessment) been completed to qualify the scope of the solution? | 06-Has a DDA (Digital Discovery Assessment) been completed to qualify the scope of the solution?
CL007 | Perform a Business Scenario and Solution Mapping | Verifies mapping of business scenarios to SAP standard solutions to assess fit-to-standard and identify configuration or extension needs. | Yes | Completed | 07 | - | CL007 | Is the customer aware of all entitlements included in their purchased subscription (for new customers, GROW Base and Premium editions) as well as any additional purchased solutions or non-standard scope items? | 07-Is the customer aware of all entitlements included in their purchased subscription (for new customers, GROW Base and Premium editions) as well as any additional purchased solutions or non-standard scope items?
CL008 | Define the Implementation Strategy | Define an implementation strategy for functional enhancements, based on the “to-be state” of the business architecture. | Yes | Completed | 09 | - | CL009 | Has the application architecture, integrations (BTP & services), and license implications been described and agreed upon with the customer? If so, please ensure this is centrally stored. | 09-Has the application architecture, integrations (BTP & services), and license implications been described and agreed upon with the customer? If so, please ensure this is centrally stored.
CL009 | Create a Strategic Road Map and Value Case | Derive a strategic roadmap for continuous improvement of SAP S/4HANA Cloud considering the findings from previous tasks. | Yes | Completed | 10 | - | CL010 | Has localization availability been checked and confirmed across all stakeholders to help mitigate gap? | 10-Has localization availability been checked and confirmed across all stakeholders to help mitigate gap?

## Prepare Quality Gate
CHECK ID | Title | Description | Answer | Status |  |  |  | Maintain Description Here | Copy Paste This Cell as Value to Column B
CL101 | Review Overview Documentation | Ensures the team has reviewed SAP S/4HANA Cloud product guides, Activate methodology, and best practices. | Yes | Completed | 01 | - | CL101 | Has the business updated the adoption backlog based on user feedback, changing business priorities etc. since the previous backlog review? | 01-Has the business updated the adoption backlog based on user feedback, changing business priorities etc. since the previous backlog review?
CL102 | Organize Provisioning Emails | Verify and confirm provisioning emails or the Initial Admin (Technical Administrator), who receives SAP credentials and upgrade info. The System and Provisioning email from SAP includes access information for the SAP Cloud ALM, SAP Central Business Configuration, SAP BTP, and SAP S/4HANA Cloud Starter Systems | Yes | Completed | 02 | - | CL102 | Have you validated the requirements and documented expert decisions for all the items in the backlog? | 02-Have you validated the requirements and documented expert decisions for all the items in the backlog?
CL103 | Ensure Project Team Members Access to the SAP Support Portal, SAP Best Practices Explorer, and SAP Customer Communities | Verifies access to SAP Support Portal, Best Practices Explorer, and Customer Communities for all team members. | Yes | Completed | 03 | - | CL103 | Has the Embedded Launch Activities (EmLA) been successfully completed for all onboarding sessions, including the review of Guided Enablement & the CQC for Transformation Assessment? | 03-Has the Embedded Launch Activities (EmLA) been successfully completed for all onboarding sessions, including the review of Guided Enablement & the CQC for Transformation Assessment?
CL104 | Request SAP Cloud ALM Tenant | Confirms the Cloud ALM tenant has been requested to manage project tasks/testing/operations. | Yes | Completed | 04 | - | CL104 | Check that an accountable customer enablement lead is managing all enablement activities throughout the Activate phases. | 04-Check that an accountable customer enablement lead is managing all enablement activities throughout the Activate phases.
CL105 | Access SAP Cloud ALM and Create Users | Verifies users have been created in Cloud ALM and team can access it. | Yes | Completed | 05 | - | CL105 | Are the customer key and end users aware of and enabled for the necessary e-Learning, including familiarity with SAP Activate, for their respective Line of Business (LoB) roles and tasks? | 05-Are the customer key and end users aware of and enabled for the necessary e-Learning, including familiarity with SAP Activate, for their respective Line of Business (LoB) roles and tasks?
CL106 | Access the SAP Central Business Configuration | Access the SAP Central Business Configuration tenant and the Administration Console of the Identity Authentication Service and perform the initial system setup. | Yes | Completed | 06 | - | CL106 | Was the enablement plan executed in preparation for the Fit-to-Standard workshops, and key users identified? | 06-Was the enablement plan executed in preparation for the Fit-to-Standard workshops, and key users identified?
CL107 | Set Up Evaluation Project in SAP Central Business Configuration | Set up and activate the Evaluation Workspace in both the Starter Customizing and Starter Development tenants of SAP Central Business Configuration. | Yes | Completed | 07 | - | CL107 | Was project initiation documentation created? For instance, the project charter, scope statement, governance model, communication & reporting mechanism, project plan, project team formulated? Please ensure this is centrally documented. | 07-Was project initiation documentation created? For instance, the project charter, scope statement, governance model, communication & reporting mechanism, project plan, project team formulated? Please ensure this is centrally documented.
CL108 | Initial System Access for SAP S/4HANA Cloud | Access the SAP S/4HANA Cloud Starter System and create the initial users of the implementation project team. Additional users can be added at any time in the future. This process is followed twice: once for the Starter Customizing tenant and once for the Starter Development tenant. | Yes | Completed | 08 | - | CL108 | Has the Strategic Adoption Planning task been completed, including the establisment of the Customer COE, the high-level, long-term plan for adopting features and functions post-go-live, and ensuring that deferred business optimizations and the multi-country rollout plan are included? | 08-Has the Strategic Adoption Planning task been completed, including the establisment of the Customer COE, the high-level, long-term plan for adopting features and functions post-go-live, and ensuring that deferred business optimizations and the multi-country rollout plan are included?
CL109 | Access Starter System and Reset Password | Confirms access to the Starter System and password resets are completed. | Yes | Completed | 09 | - | CL109 | Have you considered your organizational structure to depict clear distinction of purposes within your organization, and to support data protection regulations? | 09-Have you considered your organizational structure to depict clear distinction of purposes within your organization, and to support data protection regulations?
CL110 | Create Users in the Starter System | Verifies additional user accounts are added in Starter System, | Yes | Completed | 10 | - | CL110 | Is the Fit-to-standard workshop taking into account integrated applications and corresponding backlog items were created | 10-Is the Fit-to-standard workshop taking into account integrated applications and corresponding backlog items were created
CL111 | Self-Activation of Project Team Members in the Identity Authentication Service | Ensures team members self-activate via IAS for cloud authentication. | Yes | Completed | 11 | - | CL111 | Is there an agreed OCM concept in place that defines a common understanding of OCM for the project in terms of what, why, how and who need to address the change? | 11-Is there an agreed OCM concept in place that defines a common understanding of OCM for the project in terms of what, why, how and who need to address the change?
CL112 | Ensure Project Team Members Access to the SAP Learning Hub | Confirms team access to Learning Hub for training and certification. | Yes | Completed | 12 | - | CL112 | Have the security measures and data protection decisions defined during the Prepare phase been properly planned for implementation? | 12-Have the security measures and data protection decisions defined during the Prepare phase been properly planned for implementation?
CL113 | Ensure Project Team Members Access to the SAP Activate Community | Verifies team access to Activate Community for methodology collaboration. | Yes | Completed
CL114 | Create Self-Enablement Plan | Ensures team has a personal roadmap for self-learning and enablement. | Yes | Completed
CL115 | Review Getting Started Tutorials in S/4HANA Cloud | Confirms that introductory tutorials in S/4HANA Cloud have been reviewed. | Yes | Completed
CL116 | Create Project Schedule and Budget | Create a project schedule and budget. The project schedule defines the work to be performed, the resources and associated time commitments required, and the individual phases of the project. The work breakdown structure (WBS) serves as the foundation for the project schedule and deliverables to be produced as part of the project. | Yes | Completed
CL117 | Align Project Schedules | Ensures schedule alignment between all stakeholders including client, partner, and SAP. | Yes | Completed
CL118 | Set Up Project Team Logistics and Infrastructure | Confirms that workspaces, hardware, software, and tools are prepared. | Yes | Completed
CL119 | Verify Project Team Certification and Experience | Ensure that the project team members have at least the minimum level of knowledge and experience required to successfully implement an SAP S/4HANA Cloud system. | Yes | Completed
CL120 | Create a Document Repository for the Implementation Project Team | Set up a shared document repository for the project team to support real-time collaboration, updates, and communication. Choose a system that best fits the team's needs. | Yes | Completed
CL121 | On-board Project Team | Confirms formal onboarding with clarity on members, roles, goals, and communication protocols. | Yes | Completed
CL122 | Conduct Kickoff Workshop | Verifies the kickoff session with key stakeholders has been held to align on objectives and roles. | Yes | Completed
CL123 | Perform Initial Business Process Assessment for SAP S/4HANA Cloud | Review the customer’s current business processes to prepare for fit-to-standard workshops. Use Business Driven Configuration Questionnaires to guide discussions and document key inputs for configuration. | Yes | Completed
CL124 | Prepare for Fit-to-Standard Workshops | Verifies initial system, data, agendas, material and participants are prepared for Fit-to-Standard workshops. | Yes | Completed
CL125 | Create Initial Analytics List | Prepare and distribute the template to be used to capture notes for analytics (reports) during the fit-to-standard workshop(s). | Yes | Completed
CL126 | Create Initial Application - Workplace List | Create the initial Application - Workplace List that will be distributed to the fit-to-standard participants and used to capture notes for Identity and Access Management during the fit-to-standard workshops. The Application - Workplace List determines the application of each Scope Item and collects all required applications for the scope of the overall project. | Yes | Completed
CL127 | Review Data Protection Requirements and Functionality | Prepare to address data protection requirements and related features during fit-to-standard workshops, ensuring compliance with legal, privacy, and industry-specific regulations. | Yes | Completed
CL128 | Verify Fit-to-Standard System | Make sure all required configuration settings are in Starter Customizing Tenant in order to support discussion on selected business processes during Fit-to-Standard workshop. | Yes | Completed
CL129 | Develop the Data Migration Approach and Strategy | Confirms a preliminary strategy for data extraction, transformation, loading has been documented. (To be discussed after Fit to Standard workshop) | Yes | Completed
CL130 | Conduct Enablement Strategy Research and Interviews | Verifies that the enablement needs have been understood through workshops/research.(To be discussed after Fit to Standard workshop) | Yes | Completed
CL131 | Document Enablement Strategy | Ensures an end-user training/delivery plan has been documented.(To be discussed after Fit to Standard workshop) | Yes | Completed
CL132 | Conduct Project Quality Gate | Confirms that the Prepare phase deliverables have been reviewed and approved. | Yes | Completed
CL133 | Obtain Customer Sign-Off for Phase Completion | Verifies formal customer agreement to proceed to the next phase. | Yes | Completed