- Service Description

### ISS Obligations

ISS shall ensure that Customer shall name at least one qualified contact person for ACLOUDEAR (“Contact”) and shall provide contact details (in particular e-mail address and telephone number) by means of which the Contact or its authorized representative can be reached at any time. The Contact must be in a position to make or bring about the necessary decisions for the Customer without undue delay and shall act within the timeframes as specified in the applicable project plan. For S4HC Services that will be performed at the Customer’s facility, Customer shall make available free of charge the necessary offices, infrastructure and materials, including computers, software, telephones, fax, internet connectivity.

ACLOUDEAR/SAP needs to access the Customer’s S4HC systems for purposes of providing the SAP S4HC Services under this SOW. ISS hereby ensures that Customer grants to ACLOUDEAR the permission for such access and Customer names a contact person that –if necessary – grants to ACLOUDEAR the required access rights.

### Project Management

### ACLOUDEAR Limited Tasks and Deliverables:

- Support ISS to define the project schedule using the project schedule template provided by ISS and review with Customer.

- Coordinate ISS, Customer and ACLOUDEAR resources according to the confirmed project schedule.

- Monitor, track and report any issues and risks encountered during the Go-Live Project.

- Monitor, execute and mark as completed the activities listed in the S4HC Go-Live Activity List.

- Keep ISS fully informed of all communications with the Customer (including copying ISS on all written communications).

### ISS Responsibility towards Customer :

- Ensure the Customer set up and provide the required project infrastructure,such as WiFi in the office.

- Finalize and confirm the project schedule together with the Customer supported by ACLOUDEAR.

- Ensure all appropriate key users have been identified and allocated to the Go-Live Project

- Ensure key users and subject matter experts attend the workshops conducted by ACLOUDEAR

- Ensure timely decision making for any open questions or issues

- Perform organizational change management activities using the templates provided by ACLOUDEAR

- Manage the validation of solution readiness, data readiness and business and people readiness during all Go-Live Project phases

- Identify any issues and risks encountered during the Go-Live Project

### Q-Gate Prepare

### ACLOUDEAR Limited Tasks and Deliverables:

- Conduct an initial meeting between the Customer's Project Manager and ACLOUDEAR’s Project Manager to review project scope and preparation activities

- Conduct a project team kickoff which shall include review of project objectives, project team roles &responsibilities, and project schedule

- Confirm solution design of S4HC business scenarios utilizing workshop(s) as necessary in ACLOUDEAR’s discretion

-Confirm organizational management structure design utilizing workshop(s) as necessary in ACLOUDEAR's discretion

- Provide the “Key Users Enablement Roadmap” accelerator which includes the relevant S4HC trainings

- Review the overall data migration approach, the data migration tool and related documentation

-Introduce Customer to the ACLOUDEAR provided data migration templates

-Align the data migration project milestones with the overall project schedule

### ISS Responsibility towards Customer:

-Ensure key users complete all relevant S4HC learning tasks required for the Prepare phases specified by ACLOUDEAR Project Manager

-Provide information for the organization structure (Organizational Management) setup

-Perform data cleansing as required in the source (legacy) system(s)

-Extract data from the source (legacy) system(s)

-Complete Scope Verification

### Q-Gate Explore

### ACLOUDEAR Limited Tasks and Deliverables:

-Setup the organization structure in the S4HC Solution

-Perform the Explore activities in the S4HC Go-Live Activity List and review with ISS and Customer any activities requiring Customer input

-Perform Solution Acceptance Assessment

### ISS Responsibility towards Customer:

-Ensure key users have completed all relevant S4HC leaning tasks required for the Fine-Tune and Integrate &Extend phase as specified by SAP Project Manager

-Ensure Key Users plan and perform End User enablement

-Perform the following tasks in preparation for the Test and Go-Live phases:

:

- Populate the data migration templates with cleansed legacy data for the relevant data objects

- Perform upload of data migration templates via the S4HC Data Migration Tool with support of ACLOUDEAR Consultants

- Perform S4HC manual data entry, if applicable

- Verify and reconcile migrated data

- Provide Solution Acceptance Confirmation

### Q-Gate Realize

### ACLOUDEAR Limited Tasks and Deliverables:

-Provide the test plan and standard test scenarios based on the business scope

-Assist with preparation and adaptation of the test plan and test scenario utilizing a workshop as necessary in ACLOUDEAR’s discretion

-Assist and support ISS and the Customer with the resolution of issues related to the completion of the test plan

-Assist Customer with planning the cutover activities utilizing a workshop as necessary

-Define the cutover schedule jointly with ISS and the Customer

-Perform the Go-Live Readiness Assessment

### ISS Responsibility towards Customer:

-Ensure Key Users have completed all relevant S4HC leaning tasks required for the Test phase, as specified by the SAP Project Manager

-Modify the test plan to include any required Customer specific scenarios

-Assign test activities to responsible Key Users

-Perform integration testing and document test results in SAP provided S4HC Test Plan

-Finalize the cutover schedule and allocate resources to cutover activities

-Provide the Go-Live Readiness Acceptance confirmation

### Q-Gate Go-Live

### ACLOUDEAR Limited Tasks and Deliverables:

-Monitor and support Customer cutover activities as per the S4HC Cutover Schedule

-Prepare and issue the Acceptance Protocol for Customer sign-off

-Set S4HC Production System status to “Live”

### ISS Responsibility towards:

-Ensure Key Users and End Users have completed all relevant S4HC Leanings required for Cut over and continuous use of the S4HC Production System

-Perform organizational change management activities

-Execute cutover activities as per the S4HC Cut over Schedule

- Populate the data migration templates with cleansed legacy data for relevant data objects

- Perform upload of data migration templates via the S4HCData Migration Tool, if applicable

- Perform S4HCmanual data entry, if applicable

- Verify and reconcile migrated data

- Execute the final activities in the S4HCGo-Live Activity List

- Review, sign and return the Acceptance Protocol to ACLOUDEAR, as defined in the General Terms and Conditions