## Sheet1
Use Copy and Insert of a selected row to keep formulas consistent. |  |  | Version: | 2025-05-23
Planning Template |  |  |  |  | Project Start Date: |  | 2025-06-01
[5 empty] | Current Date |  | 2025-12-24 |  |  |  | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo | Tu | We | Th | Fr | Sa | So | Mo
No. | Title | Workstream | Duration (weeks) | Project Team | Planned Effort (hours) | Real Effort (hours) (for impl. Phase) | Start Date | End Date | do not maintain | do not maintain | time axis 2025-06-01 to 2027-02-01
1 | Discover
1.1 | Cloud Trial | Customer Team Enablement
1.1.1 | Learn on a SAP S/4HANA Cloud Trial System | Customer Team Enablement
1.2 | Partner Demonstration Landscape (Partner) | Project Management
1.2.1 | Request Demonstration Landscape | Project Management
1.3 | Discovery Assessment | Application Design and Configuration
1.3.1 | Executing a SAP Digital Discovery Assessment | Application Design and Configuration
1.3.2 | Generate SAP Digital Discovery Report | Application Design and Configuration
1.4 | Cloud Mindset Assessment | Solution Adoption
1.4.1 | Execute the Cloud Mindset | Solution Adoption
1.4.2 | Select the Right Cloud Partner | Solution Adoption
1.5 | Application Value and Scoping | Application Design and Configuration
1.5.1 | Perform a Business Scenario and Solution Mapping | Application Design and Configuration
1.5.2 | Perform Benchmarking Assessment for Value Baselining | Application Design and Configuration
1.5.3 | Define the Implementation Strategy | Application Design and Configuration
1.5.4 | Create a Strategic Road Map and Value Case | Application Design and Configuration
2 | Prepare
2.1 | Getting Started with your SAP Implementation | Project Management
2.1.1 | Review Overview Documentation | Project Management |  | ISS |  |  | 2025-06-02 | 2025-06-06 | 2025-06-02 | 2025-06-06 | bar: 2025-06-02 to 2025-06-06
2.1.2 | Organize Provisioning Emails | Technical Architecture & Infrastructure |  | ISS & HC |  |  | 2025-06-02 | 2025-06-06 | 2025-06-02 | 2025-06-06 | bar: 2025-06-02 to 2025-06-06
2.1.3 | Ensure Project Team Members Access to the SAP Support Portal, SAP Best Practices Explorer, and SAP Customer Communities | Technical Architecture & Infrastructure |  | ISS & HC |  |  | 2025-06-02 | 2025-06-06 | 2025-06-02 | 2025-06-06 | bar: 2025-06-02 to 2025-06-06
2.2 | SAP Cloud ALM Onboarding | Technical Architecture & Infrastructure
2.2.1 | Request SAP Cloud ALM Tenant | Technical Architecture & Infrastructure |  | ISS |  |  | 2025-06-02 | 2025-06-06 | 2025-06-02 | 2025-06-06 | bar: 2025-06-02 to 2025-06-06
2.2.2 | Access SAP Cloud ALM and Create Users | Technical Architecture & Infrastructure |  | ISS |  |  | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | bar: 2025-06-23 to 2025-06-30
2.3 | Initial System Access for Central Business Configuration | Technical Architecture & Infrastructure
2.3.1 | Access the SAP Central Business Configuration | Technical Architecture & Infrastructure |  | ISS |  |  | 2025-06-06 | 2025-06-12 | 2025-06-06 | 2025-06-12 | bar: 2025-06-06 to 2025-06-12
2.3.3 | Set Up Evaluation Project in SAP Central Business Configuration | Technical Architecture & Infrastructure |  | ISS |  |  | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | bar: 2025-06-09
2.4 | Initial System Access for SAP S/4HANA Cloud | Technical Architecture & Infrastructure
2.4.1 | Access Starter System and Reset Password | Technical Architecture & Infrastructure |  | ISS |  |  | 2025-06-10 | 2025-06-12 | 2025-06-10 | 2025-06-12 | bar: 2025-06-10 to 2025-06-12
2.4.2 | Create Users in the Starter System | Technical Architecture & Infrastructure |  | ISS |  |  | 2025-06-10 | 2025-06-12 | 2025-06-10 | 2025-06-12 | bar: 2025-06-10 to 2025-06-12
2.4.3 | Self-Activation of Project Team Members in the Identity Authentication Service | Technical Architecture & Infrastructure |  | ISS & HC |  |  | 2025-06-10 | 2025-06-25 | 2025-06-10 | 2025-06-25 | bar: 2025-06-10 to 2025-06-25
2.5 | SAP Supporting Implementation Tools Access | Customer Team Enablement
2.5.1 | Ensure Project Team Members Access to the SAP Learning Hub | Customer Team Enablement |  | HC |  |  | 2025-06-10 | 2025-06-25 | 2025-06-10 | 2025-06-25 | bar: 2025-06-10 to 2025-06-25
2.5.2 | Ensure Project Team Members Access to the SAP Activate Community | Project Management |  | HC |  |  | 2025-06-10 | 2025-06-25 | 2025-06-10 | 2025-06-25 | bar: 2025-06-10 to 2025-06-25
2.6 | Customer Team Self-Enablement | Customer Team Enablement
2.6.1 | Create Self-Enablement Plan | Customer Team Enablement |  | HC |  |  | 2025-06-10 | 2025-06-25 | 2025-06-10 | 2025-06-25 | bar: 2025-06-10 to 2025-06-25
2.6.2 | Review Getting Started Tutorials in S/4HANA Cloud | Customer Team Enablement |  | HC |  |  | 2025-06-10 | 2025-06-25 | 2025-06-10 | 2025-06-25 | bar: 2025-06-10 to 2025-06-25
2.7 | Project Initiation and Governance | Project Management
2.7.1 | Create Project Charter and Scope Statement | Project Management |  | ISS & HC |  |  | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | bar: 2025-06-23
2.7.3 | Define Project Communications and Reporting | Project Management |  | ISS & HC |  |  | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | bar: 2025-06-23
2.8 | Project Plans, Schedule and Budget | Integration
2.8.1 | Create Project Schedule and Budget | Project Management |  | ISS |  |  | 2025-06-18 | 2025-06-20 | 2025-06-18 | 2025-06-20 | bar: 2025-06-18 to 2025-06-20
2.8.2 | Align Project Schedules | Integration |  | ISS & HC |  |  | 2025-06-23 | 2025-06-25 | 2025-06-23 | 2025-06-25 | bar: 2025-06-23 to 2025-06-25
2.9 | Project Standards, Infrastructure, and Solution | Project Management
2.9.2 | Set Up Project Team Logistics and Infrastructure | Project Management |  | HC |  |  | 2025-06-19 | 2025-06-20 | 2025-06-19 | 2025-06-20 | bar: 2025-06-19 to 2025-06-20
2.9.3 | Verify Project Team Certification and Experience | Project Management |  | HC |  |  | 2025-06-19 | 2025-06-20 | 2025-06-19 | 2025-06-20 | bar: 2025-06-19 to 2025-06-20
2.9.4 | Create a Document Repository for the Implementation Project Team | Project Management |  | HC |  |  | 2025-06-19 | 2025-06-20 | 2025-06-19 | 2025-06-20 | bar: 2025-06-19 to 2025-06-20
2.10 | Project Kick-Off and On-Boarding | Project Management
2.10.1 | On-board Project Team | Project Management |  | ISS & HC |  |  | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | bar: 2025-06-11
2.10.2 | Conduct Kickoff Workshop | Project Management |  | ISS & HC |  |  | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | bar: 2025-06-11
2.11 | Organizational Change Management Plan | Solution Adoption
2.11.1 | Set up OCM Team and OCM Concept | Solution Adoption |  | ISS & HC |  |  | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | bar: 2025-06-23 to 2025-06-30
2.12 | Business Driven Configuration Assessment | Application Design and Configuration
2.12.1 | Perform Initial Business Process Assessment for SAP S/4HANA Cloud | Application Design and Configuration |  | HC |  |  | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | bar: 2025-06-23 to 2025-06-30
2.13 | Fit-to-Standard Analysis Preparation | Application Design and Configuration
2.13.1 | Prepare for Fit-to-Standard Workshops | Application Design and Configuration |  | ISS & HC |  |  | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | bar: 2025-06-23 to 2025-06-30
2.13.4 | Create Initial Analytics List | Analytics |  | ISS |  |  | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | bar: 2025-06-23 to 2025-06-30
2.13.5 | Create Initial Application - Workplace List | Application Design and Configuration |  | ISS |  |  | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | bar: 2025-06-23 to 2025-06-30
2.13.6 | Review Data Protection Requirements and Functionality | Application Design and Configuration |  | ISS |  |  | 2025-06-23 | 2025-06-30 | 2025-06-23 | 2025-06-30 | bar: 2025-06-23 to 2025-06-30
2.14 | Fit-to-Standard System Preparation | Application Design and Configuration
2.14.1 | Verify Fit-to-Standard System | Application Design and Configuration |  | ISS |  |  | 2025-06-25 | 2025-06-27 | 2025-06-25 | 2025-06-27 | bar: 2025-06-25 to 2025-06-27
2.15 | Data Migration Approach and Strategy | Data Management
2.15.1 | Develop the Data Migration Approach and Strategy | Data Management |  | ISS & HC |  |  | 2025-06-25 | 2025-06-27 | 2025-06-25 | 2025-06-27 | bar: 2025-06-25 to 2025-06-27
2.16 | Enablement Strategy | Solution Adoption
2.16.1 | Conduct Enablement Strategy Research and Interviews | Solution Adoption |  | ISS & HC |  |  | 2025-06-23 | 2025-06-25 | 2025-06-23 | 2025-06-25 | bar: 2025-06-23 to 2025-06-25
2.16.2 | Document Enablement Strategy | Solution Adoption |  | ISS & HC |  |  | 2025-06-23 | 2025-06-27 | 2025-06-23 | 2025-06-27 | bar: 2025-06-23 to 2025-06-27
2.19 | Phase Closure and Sign-Off Phase Deliverables | Project Management
2.19.1 | Conduct Project Quality Gate | Project Management |  | ISS & HC |  |  | 2025-06-25 | 2025-06-27 | 2025-06-25 | 2025-06-27 | bar: 2025-06-25 to 2025-06-27
2.19.2 | Obtain Customer Sign-Off for Phase Completion | Project Management |  | ISS & HC |  |  | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | bar: 2025-06-28
3 | Explore
3.1 | Execution/Monitoring of Project | Project Management
3.1.1 | Direct and Manage Project Execution | Project Management |  | ISS & HC |  |  | 2025-06-28 | 2025-08-08 | 2025-06-28 | 2025-08-08 | bar: 2025-06-28 to 2025-08-08
3.1.2 | Update Project Management Documents | Project Management |  | ISS & HC |  |  | 2025-06-28 | 2025-08-08 | 2025-06-28 | 2025-08-08 | bar: 2025-06-28 to 2025-08-08
3.1.3 | Manage Project Issues, Risks, and Changes | Project Management |  | ISS & HC |  |  | 2025-06-28 | 2025-08-08 | 2025-06-28 | 2025-08-08 | bar: 2025-06-28 to 2025-08-08
3.1.4 | Communicate Project Status and Progress | Project Management |  | ISS & HC
3.2 | Fit-to-Standard Analysis | Application Design and Configuration
3.2.1 | Schedule Fit-to-Standard Workshops | Application Design and Configuration |  | ISS & HC |  |  | 2025-07-07 | 2025-07-18 | 2025-07-07 | 2025-07-18 | bar: 2025-07-07 to 2025-07-18
3.2.2 | Chart of Accounts - Conduct Workshop | Application Design and Configuration |  | ISS & HC |  |  | 2025-07-07 | 2025-07-18 | 2025-07-07 | 2025-07-18 | bar: 2025-07-07 to 2025-07-18
3.2.3 | Organizational Structure - Conduct Workshop | Application Design and Configuration |  | ISS & HC |  |  | 2025-07-07 | 2025-07-18 | 2025-07-07 | 2025-07-18 | bar: 2025-07-07 to 2025-07-18
3.2.4 | Finance - Conduct Workshop | Application Design and Configuration |  | ISS & HC |  |  | 2025-07-07 | 2025-07-18 | 2025-07-07 | 2025-07-18 | bar: 2025-07-07 to 2025-07-18
3.2.5 | Human Resources - Conduct Workshop | Application Design and Configuration |  | ISS & HC |  |  | 2025-07-07 | 2025-07-18 | 2025-07-07 | 2025-07-18 | bar: 2025-07-07 to 2025-07-18
3.2.6 | Sales - Conduct Workshop | Application Design and Configuration |  | ISS & HC |  |  | 2025-07-07 | 2025-07-18 | 2025-07-07 | 2025-07-18 | bar: 2025-07-07 to 2025-07-18
3.2.7 | Sourcing and Procurement - Conduct Workshop | Application Design and Configuration |  | ISS & HC |  |  | 2025-07-07 | 2025-07-18 | 2025-07-07 | 2025-07-18 | bar: 2025-07-07 to 2025-07-18
3.2.8 | Manufacturing - Conduct Workshop | Application Design and Configuration |  | ISS & HC |  |  | 2025-07-07 | 2025-07-18 | 2025-07-07 | 2025-07-18 | bar: 2025-07-07 to 2025-07-18
3.2.9 | Professional Services - Conduct Workshop | Application Design and Configuration |  | ISS & HC |  |  | 2025-07-07 | 2025-07-18 | 2025-07-07 | 2025-07-18 | bar: 2025-07-07 to 2025-07-18
3.2.10 | R&D Engineering - Conduct Workshop | Application Design and Configuration |  | ISS & HC |  |  | 2025-07-07 | 2025-07-18 | 2025-07-07 | 2025-07-18 | bar: 2025-07-07 to 2025-07-18
3.2.11 | Supply Chain - Conduct Workshop | Application Design and Configuration |  | ISS & HC |  |  | 2025-07-07 | 2025-07-18 | 2025-07-07 | 2025-07-18 | bar: 2025-07-07 to 2025-07-18
3.2.12 | Service - Conduct Workshop | Application Design and Configuration |  | ISS & HC |  |  | 2025-07-07 | 2025-07-18 | 2025-07-07 | 2025-07-18 | bar: 2025-07-07 to 2025-07-18
3.2.13 | Asset Management - Conduct Workshop | Application Design and Configuration |  | ISS & HC |  |  | 2025-07-07 | 2025-07-18 | 2025-07-07 | 2025-07-18 | bar: 2025-07-07 to 2025-07-18
3.3 | Customer Execution of Standard Processes | Customer Team Enablement
3.3.1 | Execute Standard Business Processes | Customer Team Enablement |  | ISS & HC |  |  | 2025-07-21 | 2025-07-25 | 2025-07-21 | 2025-07-25 | bar: 2025-07-21 to 2025-07-25
3.4 | Fit-to-Standard Analysis Documentation | Application Design and Configuration
3.4.1 | Document Initial Configuration Settings for SAP Central Business Configuration | Application Design and Configuration |  | ISS |  |  | 2025-07-21 | 2025-07-25 | 2025-07-21 | 2025-07-25 | bar: 2025-07-21 to 2025-07-25
3.4.14 | Confirm Backlog | Application Design and Configuration |  | ISS & HC |  |  | 2025-07-24 | 2025-07-25 | 2025-07-24 | 2025-07-25 | bar: 2025-07-24 to 2025-07-25
3.5 | Integration Planning and Design | Integration
3.5.1 | Handover of Requirements to Integration Expert | Integration |  | ISS |  |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-31 | bar: 2025-07-28 to 2025-07-31
3.5.2 | Determine Scenario Options for Integrations | Integration |  | ISS & HC |  |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-31 | bar: 2025-07-28 to 2025-07-31
3.5.3 | Determine Details for Customer-Driven Integrations | Integration |  | ISS & HC |  |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-31 | bar: 2025-07-28 to 2025-07-31
3.5.4 | Determine Details for Customer-Driven Integrations using Open Connectors | Integration |  | ISS & HC |  |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-31 | bar: 2025-07-28 to 2025-07-31
3.5.7 | Optimize and Align Integration Scenario List | Integration |  | ISS |  |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-31 | bar: 2025-07-28 to 2025-07-31
3.5.8 | Review and Customer Sign-off List of Integrations | Integration |  | ISS & HC |  |  | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | bar: 2025-07-31
3.6 | Extension Planning and Design | Extensibility
3.6.1 | Handover of Requirements for Extensions to Developer | Extensibility |  | ISS |  |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-31 | bar: 2025-07-28 to 2025-07-31
3.6.4 | Collect Details for Extensions | Extensibility |  | ISS & HC |  |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-31 | bar: 2025-07-28 to 2025-07-31
3.6.5 | Detail Design on Key-User Extensibility | Extensibility |  | ISS & HC |  |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-31 | bar: 2025-07-28 to 2025-07-31
3.6.7 | Review and Sign off Design of Extension | Extensibility
3.7 | Analytics Planning and Design | Analytics
3.7.1 | Handover of Requirements to Analytics Expert | Analytics |  | ISS |  |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-31 | bar: 2025-07-28 to 2025-07-31
3.7.2 | Review Scope Items and Requirements for Embedded Analytics | Analytics |  | ISS & HC |  |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-31 | bar: 2025-07-28 to 2025-07-31
3.7.3 | Review Scope Items and Requirements for Strategic Analytics (Optional) | Analytics |  | ISS & HC |  |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-31 | bar: 2025-07-28 to 2025-07-31
3.7.4 | Determine Extensions of Reports | Analytics |  | ISS & HC |  |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-31 | bar: 2025-07-28 to 2025-07-31
3.7.5 | Determine Details for Customer-Driven Analytics | Analytics |  | ISS & HC |  |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-31 | bar: 2025-07-28 to 2025-07-31
3.7.6 | Review and Customer Sign off for Analytics | Analytics |  | HC |  |  | 2025-08-01 | 2025-08-04 | 2025-08-01 | 2025-08-04 | bar: 2025-08-01 to 2025-08-04
3.8 | Artificial Intelligence Planning and Design | Integration
3.9 | Artificial Intelligence Setup | Integration
3.10 | Identity and Access Management Planning and Design | Application Design and Configuration
3.10.1 | Plan and Design Identity and Access Management | Application Design and Configuration |  | ISS & HC |  |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-31 | bar: 2025-07-28 to 2025-07-31
3.11 | New Scope Activation via SAP Central Business Configuration | Application Design and Configuration
3.11.1 | Verify Requirements for New Country/Region | Application Design and Configuration |  | ISS & HC |  |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-31 | bar: 2025-07-28 to 2025-07-31
3.11.2 | Set Up Exchange Rates for New Country/Region | Application Design and Configuration |  | ISS & HC |  |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-31 | bar: 2025-07-28 to 2025-07-31
3.11.3 | Request New Scope or Country/Region Activation via SAP Central Business Configuration | Application Design and Configuration |  | ISS |  |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-31 | bar: 2025-07-28 to 2025-07-31
3.11.4 | Revise Business Roles and Business Catalogs | Technical Architecture & Infrastructure |  | ISS & HC |  |  | 2025-07-28 | 2025-07-31 | 2025-07-28 | 2025-07-31 | bar: 2025-07-28 to 2025-07-31
3.12 | Learning Needs Analysis for Users | Solution Adoption
3.12.1 | Identify Learning Needs | Solution Adoption |  | HC |  |  | 2025-08-01 | 2025-08-08 | 2025-08-01 | 2025-08-08 | bar: 2025-08-01 to 2025-08-08
3.12.2 | Create Learning Curriculum | Solution Adoption |  | HC |  |  | 2025-08-01 | 2025-08-08 | 2025-08-01 | 2025-08-08 | bar: 2025-08-01 to 2025-08-08
3.12.3 | Conduct Enablement Business Review | Solution Adoption |  | HC |  |  | 2025-08-01 | 2025-08-08 | 2025-08-01 | 2025-08-08 | bar: 2025-08-01 to 2025-08-08
3.13 | Data Load Preparation | Data Management
3.13.1 | Determine the Required Master Data and Transactional Data for S/4HANA Cloud | Data Management |  | ISS & HC |  |  | 2025-08-01 | 2025-08-08 | 2025-08-01 | 2025-08-08 | bar: 2025-08-01 to 2025-08-08
3.13.2 | Determine Migration Cockpit Field Structures for S/4HANA Cloud | Data Management |  | ISS & HC |  |  | 2025-08-01 | 2025-08-08 | 2025-08-01 | 2025-08-08 | bar: 2025-08-01 to 2025-08-08
3.13.3 | Define Specifications for Data Extraction from a Legacy System | Data Management |  | ISS & HC |  |  | 2025-08-01 | 2025-08-08 | 2025-08-01 | 2025-08-08 | bar: 2025-08-01 to 2025-08-08
3.13.4 | Perform Data Cleansing Activities | Data Management |  | HC
3.14 | Test Planning | Testing
3.14.1 | Create Test Strategy | Testing |  | ISS & HC |  |  | 2025-08-01 | 2025-08-08 | 2025-08-01 | 2025-08-08 | bar: 2025-08-01 to 2025-08-08
3.14.2 | Create and Schedule Test Plan | Testing |  | ISS & HC |  |  | 2025-08-01 | 2025-08-08 | 2025-08-01 | 2025-08-08 | bar: 2025-08-01 to 2025-08-08
3.14.3 | Determine Test Scope | Testing |  | ISS & HC |  |  | 2025-08-01 | 2025-08-08 | 2025-08-01 | 2025-08-08 | bar: 2025-08-01 to 2025-08-08
3.15 | Organizational Change Management Impact Analysis | Solution Adoption
3.16 | Phase Closure and Sign-Off Phase Deliverables | Project Management
3.16.1 | Conduct Project Quality Gate | Project Management |  | ISS & HC |  |  | 2025-08-07 | 2025-08-08 | 2025-08-07 | 2025-08-08 | bar: 2025-08-07 to 2025-08-08
3.16.2 | Obtain Customer Sign-Off for Phase Completion | Project Management |  | ISS & HC |  |  | 2025-08-07 | 2025-08-08 | 2025-08-07 | 2025-08-08 | bar: 2025-08-07 to 2025-08-08
4 | Realize
4.1 | Execution/Monitoring of Project | Project Management
4.1.1 | Direct and Manage Project Execution | Project Management |  | ISS & HC |  |  | 2025-08-11 | 2025-11-17 | 2025-08-11 | 2025-11-17 | bar: 2025-08-11 to 2025-11-17
4.1.2 | Update Project Management Documents | Project Management |  | ISS & HC |  |  | 2025-08-11 | 2025-11-17 | 2025-08-11 | 2025-11-17 | bar: 2025-08-11 to 2025-11-17
4.1.3 | Plan and Execute Agile Sprints | Project Management |  | ISS & HC |  |  | 2025-08-11 | 2025-11-17 | 2025-08-11 | 2025-11-17 | bar: 2025-08-11 to 2025-11-17
4.1.4 | Manage Project Issues, Risks, and Changes | Project Management |  | ISS & HC |  |  | 2025-08-11 | 2025-11-17 | 2025-08-11 | 2025-11-17 | bar: 2025-08-11 to 2025-11-17
4.1.5 | Communicate Project Status and Progress | Project Management |  | ISS & HC |  |  | 2025-08-11 | 2025-11-17 | 2025-08-11 | 2025-11-17 | bar: 2025-08-11 to 2025-11-17
4.2 | OCM Alignment Activities | Solution Adoption
4.3 | Initial Quality System Setup | Integration
4.3.1 | Execute Initial Setup of the Quality System | Technical Architecture & Infrastructure |  | ISS |  |  | 2025-08-11 | 2025-08-12 | 2025-08-11 | 2025-08-12 | bar: 2025-08-11 to 2025-08-12
4.4 | Quality System Initial Access | Technical Architecture & Infrastructure
4.4.1 | Receive Quality System and Reset Password | Technical Architecture & Infrastructure |  | ISS |  |  | 2025-08-12 | 2025-08-13 | 2025-08-12 | 2025-08-13 | bar: 2025-08-12 to 2025-08-13
4.4.2 | Adapt Configuration Expert Role | Technical Architecture & Infrastructure |  | ISS |  |  | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | bar: 2025-08-13
4.4.3 | Create Users in the Quality System | Technical Architecture & Infrastructure |  | ISS |  |  | 2025-08-13 | 2025-08-14 | 2025-08-13 | 2025-08-14 | bar: 2025-08-13 to 2025-08-14
4.4.4 | Self-Activation of Project Team Members in the Identity Authentication Service | Technical Architecture & Infrastructure |  | ISS & HC |  |  | 2025-08-14 | 2025-08-15 | 2025-08-14 | 2025-08-15 | bar: 2025-08-14 to 2025-08-15
4.5 | Production System Request | Technical Architecture & Infrastructure
4.5.1 | Request the Production System | Technical Architecture & Infrastructure |  | ISS & HC
4.5.2 | Request Access to the SAP S/4HANA Cloud Release Assessment Tool | Technical Architecture & Infrastructure |  | ISS & HC
4.6 | Production System Initial Access | Technical Architecture & Infrastructure
4.6.1 | Receive Production System and Reset Password | Technical Architecture & Infrastructure |  | ISS & HC
4.6.2 | Transport Initial Change Project from Q-System to P-System | Technical Architecture & Infrastructure |  | ISS
4.6.3 | Create Users in the Production System | Technical Architecture & Infrastructure |  | ISS
4.6.4 | Self-Activation of Project Team Members in the Identity Authentication Service | Technical Architecture & Infrastructure |  | ISS
4.7 | Enablement Content Development | Solution Adoption
4.7.1 | Create a Content Development Plan | Solution Adoption |  | HC |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 | 2025-08-29 | bar: 2025-08-18 to 2025-08-29
4.7.2 | Manage Content Design and Content Development | Solution Adoption |  | HC |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 | 2025-08-29 | bar: 2025-08-18 to 2025-08-29
4.8 | Required Configuration Before System Use - SAP S/4HANA Cloud | Application Design and Configuration
4.8.1 | Configure Tax Solution | Application Design and Configuration |  | ISS |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 | 2025-08-29 | bar: 2025-08-18 to 2025-08-29
4.8.2 | Adapt Chart of Accounts | Application Design and Configuration |  | ISS |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 | 2025-08-29 | bar: 2025-08-18 to 2025-08-29
4.8.3 | Maintain Profit Center Configuration | Application Design and Configuration |  | ISS |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 | 2025-08-29 | bar: 2025-08-18 to 2025-08-29
4.8.4 | Maintain Cost Center Master Data | Application Design and Configuration |  | ISS |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 | 2025-08-29 | bar: 2025-08-18 to 2025-08-29
4.8.5 | Maintain Takeover Date Information for Asset Accounting | Application Design and Configuration |  | ISS |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 | 2025-08-29 | bar: 2025-08-18 to 2025-08-29
4.9 | Standard Integration Setup in the Quality/Test Landscape | Integration
4.9.2 | Set Up Integration using Cloud Integration Automation Service (CIAS) | Integration |  | ISS |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 | 2025-08-29 | bar: 2025-08-18 to 2025-08-29
4.9.3 | Set Up Integrations in the Quality/Test System | Integration |  | ISS |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 | 2025-08-29 | bar: 2025-08-18 to 2025-08-29
4.10 | Solution Configuration | Application Design and Configuration
4.10.1 | Maintain Additional G/L Accounts | Application Design and Configuration |  | ISS |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 | 2025-08-29 | bar: 2025-08-18 to 2025-08-29
4.10.2 | Configure SAP S/4HANA Cloud | Application Design and Configuration |  | ISS |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 | 2025-08-29 | bar: 2025-08-18 to 2025-08-29
4.10.3 | Request Expert Configuration | Application Design and Configuration |  | ISS |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 | 2025-08-29 | bar: 2025-08-18 to 2025-08-29
4.10.4 | Track Changes in Configuration | Application Design and Configuration |  | ISS |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 | 2025-08-29 | bar: 2025-08-18 to 2025-08-29
4.10.5 | Execute Business Process Unit Test | Application Design and Configuration |  | ISS |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 | 2025-08-29 | bar: 2025-08-18 to 2025-08-29
4.10.6 | Transport Configuration | Application Design and Configuration |  | ISS |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 | 2025-08-29 | bar: 2025-08-18 to 2025-08-29
4.10.7 | Perform Manual Rework on Production System | Application Design and Configuration |  | ISS |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 | 2025-08-29 | bar: 2025-08-18 to 2025-08-29
4.10.8 | Verify Configuration with Business Process Requirements | Application Design and Configuration |  | ISS |  |  | 2025-08-18 | 2025-08-29 | 2025-08-18 | 2025-08-29 | bar: 2025-08-18 to 2025-08-29
4.11 | New Scope Activation via SAP Central Business Configuration | Application Design and Configuration
4.11.1 | Verify Requirements for New Country/Region | Application Design and Configuration |  | ISS & HC |  |  | 2025-09-01 | 2025-09-09 | 2025-09-01 | 2025-09-09 | bar: 2025-09-01 to 2025-09-09
4.11.2 | Set Up Exchange Rates for New Country/Region | Application Design and Configuration |  | ISS & HC |  |  | 2025-09-01 | 2025-09-09 | 2025-09-01 | 2025-09-09 | bar: 2025-09-01 to 2025-09-09
4.11.3 | Request New Scope or Country/Region Activation via SAP Central Business Configuration | Application Design and Configuration |  | ISS |  |  | 2025-09-01 | 2025-09-09 | 2025-09-01 | 2025-09-09 | bar: 2025-09-01 to 2025-09-09
4.11.4 | Revise Business Roles and Business Catalogs | Technical Architecture & Infrastructure |  | ISS & HC |  |  | 2025-09-01 | 2025-09-09 | 2025-09-01 | 2025-09-09 | bar: 2025-09-01 to 2025-09-09
4.12 | New Scope Item Activation for Manage Your Solution App | Application Design and Configuration
4.12.1 | Review and Request New Scope Activation for Manage Your Solution App | Application Design and Configuration |  | ISS |  |  | 2025-09-10 | 2025-09-12 | 2025-09-10 | 2025-09-12 | bar: 2025-09-10 to 2025-09-12
4.12.2 | Revise Business Roles and Business Catalogs | Technical Architecture & Infrastructure |  | ISS & HC |  |  | 2025-09-10 | 2025-09-12 | 2025-09-10 | 2025-09-12 | bar: 2025-09-10 to 2025-09-12
4.13 | New Country/Region Expansion for Manage Your Solution App | Application Design and Configuration
4.13.1 | Verify Requirements for New Country/Region | Application Design and Configuration |  | ISS & HC |  |  | 2025-09-15 | 2025-09-19 | 2025-09-15 | 2025-09-19 | bar: 2025-09-15 to 2025-09-19
4.13.2 | Set Up Exchange Rates for New Country/Region | Application Design and Configuration |  | ISS & HC |  |  | 2025-09-15 | 2025-09-19 | 2025-09-15 | 2025-09-19 | bar: 2025-09-15 to 2025-09-19
4.13.3 | Extend Solution to Include a New Country/Region for Manage Your Solution App | Application Design and Configuration |  | ISS |  |  | 2025-09-15 | 2025-09-19 | 2025-09-15 | 2025-09-19 | bar: 2025-09-15 to 2025-09-19
4.14 | Release and Update Cycles for SAP S/4HANA Cloud | Application Design and Configuration
4.15 | Setup Instructions for Customer Driven Integrations | Integration
4.15.1 | Write Setup Instructions for Customer Driven Integrations | Integration |  | ISS |  |  | 2025-09-22 | 2025-10-03 | 2025-09-22 | 2025-10-03 | bar: 2025-09-22 to 2025-10-03
4.16 | Artificial Intelligence setup in Q-landscape | Integration
4.17 | Analytics Configuration in the Quality System | Analytics
4.17.1 | Configure Analytics in the Quality System | Analytics |  | ISS |  |  | 2025-09-22 | 2025-10-03 | 2025-09-22 | 2025-10-03 | bar: 2025-09-22 to 2025-10-03
4.18 | Identity and Access Management Configuration in the Quality/Test System | Application Design and Configuration
4.18.1 | Configure Identity and Access Management in the Q-System | Application Design and Configuration |  | ISS |  |  | 2025-09-22 | 2025-10-03 | 2025-09-22 | 2025-10-03 | bar: 2025-09-22 to 2025-10-03
4.19 | Output Management Setup in the Quality/Test System | Application Design and Configuration
4.19.1 | Set Up Printers | Application Design and Configuration |  | HC |  |  | 2025-09-22 | 2025-10-03 | 2025-09-22 | 2025-10-03 | bar: 2025-09-22 to 2025-10-03
4.19.2 | Set Up Email | Application Design and Configuration |  | HC |  |  | 2025-09-22 | 2025-10-03 | 2025-09-22 | 2025-10-03 | bar: 2025-09-22 to 2025-10-03
4.19.3 | Customize Form Templates | Application Design and Configuration |  | ISS |  |  | 2025-09-22 | 2025-10-03 | 2025-09-22 | 2025-10-03 | bar: 2025-09-22 to 2025-10-03
4.19.4 | Customize Email Templates | Application Design and Configuration |  | ISS |  |  | 2025-09-22 | 2025-10-03 | 2025-09-22 | 2025-10-03 | bar: 2025-09-22 to 2025-10-03
4.19.5 | Transport Custom Objects from Quality to Productive System | Application Design and Configuration |  | ISS |  |  | 2025-09-22 | 2025-10-03 | 2025-09-22 | 2025-10-03 | bar: 2025-09-22 to 2025-10-03
4.20 | Development and Setup of Extensions in Quality/Test System | Extensibility
4.20.1 | Setup and Develop Key-User Extensions | Extensibility |  | ISS |  |  | 2025-09-22 | 2025-10-03 | 2025-09-22 | 2025-10-03 | bar: 2025-09-22 to 2025-10-03
4.21 | Standard Integration Setup in the Production Landscape | Integration
4.21.1 | Set Up Integration in the P-Landscape using Cloud Integration Automation Service (CIAS) | Integration |  | ISS |  |  | 2025-09-22 | 2025-10-03 | 2025-09-22 | 2025-10-03 | bar: 2025-09-22 to 2025-10-03
4.21.2 | Set Up Employee Central Integration (JB1) | Integration |  | ISS |  |  | 2025-09-22 | 2025-10-03 | 2025-09-22 | 2025-10-03 | bar: 2025-09-22 to 2025-10-03
4.21.3 | Set Up Integrations in the Productive Landscape | Integration |  | ISS |  |  | 2025-09-22 | 2025-10-03 | 2025-09-22 | 2025-10-03 | bar: 2025-09-22 to 2025-10-03
4.22 | Artificial Intelligence Setup in Productive Landscape | Integration
4.23 | Solution Walkthrough | Application Design and Configuration
4.23.1 | Prepare for Solution Walkthrough | Application Design and Configuration |  | ISS |  |  | 2025-10-06 | 2025-10-10 | 2025-10-06 | 2025-10-10 | bar: 2025-10-06 to 2025-10-10
4.23.2 | Conduct Solution Walkthrough | Application Design and Configuration |  | ISS |  |  | 2025-10-13 | 2025-10-24 | 2025-10-13 | 2025-10-24 | bar: 2025-10-13 to 2025-10-24
4.24 | Test Preparation for SAP S/4HANA Cloud | Testing
4.24.1 | Prepare Testing Prerequisites | Testing |  | ISS |  |  | 2025-10-27 | 2025-10-31 | 2025-10-27 | 2025-10-31 | bar: 2025-10-27 to 2025-10-31
4.24.2 | Set Up Selected Third Party Automated Testing Tools | Testing |  | ISS |  |  | 2025-10-27 | 2025-10-31 | 2025-10-27 | 2025-10-31 | bar: 2025-10-27 to 2025-10-31
4.24.3 | Set Up Users for the Test Automation Tool | Testing |  | ISS |  |  | 2025-10-27 | 2025-10-31 | 2025-10-27 | 2025-10-31 | bar: 2025-10-27 to 2025-10-31
4.24.4 | Define a Test Case | Testing |  | ISS & HC |  |  | 2025-10-27 | 2025-10-31 | 2025-10-27 | 2025-10-31 | bar: 2025-10-27 to 2025-10-31
4.24.5 | Create Test Process (Test Case) | Testing |  | ISS & HC |  |  | 2025-10-27 | 2025-10-31 | 2025-10-27 | 2025-10-31 | bar: 2025-10-27 to 2025-10-31
4.24.6 | Create Manual Test Cases | Testing |  | ISS & HC |  |  | 2025-10-27 | 2025-10-31 | 2025-10-27 | 2025-10-31 | bar: 2025-10-27 to 2025-10-31
4.24.7 | Create Test Plan | Testing |  | ISS & HC |  |  | 2025-10-27 | 2025-10-31 | 2025-10-27 | 2025-10-31 | bar: 2025-10-27 to 2025-10-31
4.24.8 | Change Test Data Using Data Variant | Testing |  | ISS & HC |  |  | 2025-10-27 | 2025-10-31 | 2025-10-27 | 2025-10-31 | bar: 2025-10-27 to 2025-10-31
4.24.9 | Create Test Process with Test Automation Tool | Testing |  | ISS & HC |  |  | 2025-10-27 | 2025-10-31 | 2025-10-27 | 2025-10-31 | bar: 2025-10-27 to 2025-10-31
4.24.10 | Create Test Process with Selected Testing Tools | Testing |  | ISS & HC |  |  | 2025-10-27 | 2025-10-31 | 2025-10-27 | 2025-10-31 | bar: 2025-10-27 to 2025-10-31
4.24.11 | Edit Action Data and Change Visibility of Test Process | Testing |  |  |  |  | 2025-10-27 | 2025-10-31 | 2025-10-27 | 2025-10-31 | bar: 2025-10-27 to 2025-10-31
4.25 | Data Migration into the Quality/Test Tenant | Data Management
4.25.1 | Execute Data Migration Using Staging Tables | Data Management |  | ISS |  |  | 2025-11-03 | 2025-11-07 | 2025-11-03 | 2025-11-07 | bar: 2025-11-03 to 2025-11-07
4.25.2 | Conduct Final Data Quality Assessment | Data Management |  | ISS |  |  | 2025-11-03 | 2025-11-07 | 2025-11-03 | 2025-11-07 | bar: 2025-11-03 to 2025-11-07
4.26 | Automated Test Execution for SAP S/4HANA Cloud | Testing
4.26.1 | Execute the Test Plan | Testing |  | ISS & HC |  |  | 2025-11-03 | 2025-11-07 | 2025-11-03 | 2025-11-07 | bar: 2025-11-03 to 2025-11-07
4.26.2 | Correct and Re-run Test Plan | Testing |  | ISS & HC |  |  | 2025-11-06 | 2025-11-10 | 2025-11-06 | 2025-11-10 | bar: 2025-11-06 to 2025-11-10
4.26.3 | Test Execution Analysis and Reporting | Testing |  | ISS & HC |  |  | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-11 | bar: 2025-11-10 to 2025-11-11
4.27 | Enablement Delivery | Solution Adoption
4.27.1 | Train the Trainer | Solution Adoption |  | ISS & HC |  |  | 2025-11-10 | 2025-11-14 | 2025-11-10 | 2025-11-14 | bar: 2025-11-10 to 2025-11-14
4.27.2 | Plan Learning Logistics | Solution Adoption |  | ISS & HC |  |  | 2025-11-10 | 2025-11-14 | 2025-11-10 | 2025-11-14 | bar: 2025-11-10 to 2025-11-14
4.27.3 | Deliver Enablement | Solution Adoption |  | ISS & HC |  |  | 2025-11-10 | 2025-11-21 | 2025-11-10 | 2025-11-21 | bar: 2025-11-10 to 2025-11-21
4.28 | Support Operations and Handover Plan | Operations and Support
4.28.1 | Establish Support and Operation Processes | Operations and Support |  | ISS & HC |  |  | 2025-11-03 | 2025-11-07 | 2025-11-03 | 2025-11-07 | bar: 2025-11-03 to 2025-11-07
4.29 | Cutover Preparation | Data Management
4.29.1 | Create Cutover Plan and Documentation | Data Management |  | ISS & HC |  |  | 2025-11-03 | 2025-11-07 | 2025-11-03 | 2025-11-07 | bar: 2025-11-03 to 2025-11-07
4.30 | Analytics Configuration in the Production System | Analytics
4.30.1 | Configure Analytics in the Production System | Analytics |  | ISS |  |  | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-17 | bar: 2025-11-10 to 2025-11-17
4.31 | Solution Extension Deployment on Production | Extensibility
4.31.1 | Deploy Solution Extensions | Extensibility |  | ISS |  |  | 2025-11-10 | 2025-11-17 | 2025-11-10 | 2025-11-17 | bar: 2025-11-10 to 2025-11-17
4.32 | Phase Closure and Sign-Off Phase Deliverables | Project Management
4.32.1 | Conduct Project Quality Gate | Project Management |  | ISS & HC |  |  | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | bar: 2025-11-17
4.32.2 | Obtain Customer Sign-Off for Phase Completion | Project Management |  | ISS & HC |  |  | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | bar: 2025-11-17
5 | Deploy
5.1 | Execution/Monitoring of Project | Project Management |  | ISS & HC |  |  | 2025-11-18 | 2025-12-12 | 2025-11-18 | 2025-12-12 | bar: 2025-11-18 to 2025-12-12
5.1.1 | Direct and Manage Project Execution | Project Management |  | ISS & HC |  |  | 2025-11-18 | 2025-12-12 | 2025-11-18 | 2025-12-12 | bar: 2025-11-18 to 2025-12-12
5.1.2 | Update Project Management Documents | Project Management |  | ISS & HC |  |  | 2025-11-18 | 2025-12-12 | 2025-11-18 | 2025-12-12 | bar: 2025-11-18 to 2025-12-12
5.1.3 | Manage Project Issues, Risks, and Changes | Project Management |  | ISS & HC |  |  | 2025-11-18 | 2025-12-12 | 2025-11-18 | 2025-12-12 | bar: 2025-11-18 to 2025-12-12
5.1.4 | Communicate Project Status and Progress | Project Management |  | ISS & HC |  |  | 2025-11-18 | 2025-12-12 | 2025-11-18 | 2025-12-12 | bar: 2025-11-18 to 2025-12-12
5.2 | OCM Execution Activities | Solution Adoption
5.3 | Production Cutover | Integration
5.3.1 | Verify Non-Transportable Set-up | Data Management |  | ISS & HC
5.3.2 | Execute Cutover Tasks per the Cutover Plan | Data Management |  | ISS & HC |  |  | 2025-11-14 | 2025-11-28 | 2025-11-14 | 2025-11-28 | bar: 2025-11-14 to 2025-11-28
5.4 | System Go-Live | Technical Architecture & Infrastructure
5.4.1 | Set Production System to Live | Technical Architecture & Infrastructure |  | ISS & HC |  |  | 2025-12-02 | 2025-12-03 | 2025-12-02 | 2025-12-03 | bar: 2025-12-02 to 2025-12-03
5.5 | Phase Closure and Sign-Off Phase Deliverables | Project Management
5.5.1 | Conduct Project Quality Gate | Project Management |  | ISS & HC |  |  | 2025-12-08 | 2025-12-12 | 2025-12-08 | 2025-12-12 | bar: 2025-12-08 to 2025-12-12
5.5.2 | Obtain Customer Sign-Off for Phase/Project Completion | Project Management |  | ISS & HC |  |  | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | bar: 2025-12-12
6 | Run
6.1 | Ongoing System Operations | Integration
6.1.1 | Manage Posting Periods | Technical Architecture & Infrastructure
6.1.2 | Check External Tax Partner Interface | Technical Architecture & Infrastructure
6.1.5 | Access SAP Support Service | Operations and Support
6.1.6 | Evaluate and Request Test Data Refresh Service | Operations and Support
6.2 | OCM Continuous Change Management Activities | Solution Adoption
6.3 | User Experience Management Tool Deployment | Solution Adoption
6.3.1 | Execute Technical Implementation | Solution Adoption
6.4 | Release and Update Cycles for SAP S/4HANA Cloud | Application Design and Configuration
6.5 | Regression Test for SAP S/4HANA Cloud Upgrade | Testing
6.6 | Continuous Improvement | Application Design and Configuration
6.6.1 | Transport Configuration | Application Design and Configuration
6.6.2 | Evaluate Need for Test Tenant | Technical Architecture & Infrastructure
6.6.3 | Evaluate Need for Situation Handling Types | Application Design and Configuration
6.6.4 | Participate in the SAP Customer Influence Council | Application Design and Configuration
6.6.5 | Perform a Business Scenario and Solution Mapping | Application Design and Configuration
6.6.6 | Perform Benchmarking Assessment for Value Realization Comparison | Application Design and Configuration
6.7 | New Scope Activation via SAP Central Business Configuration | Application Design and Configuration
6.7.1 | Verify Requirements for New Country/Region | Application Design and Configuration
6.7.2 | Set Up Exchange Rates for New Country/Region | Application Design and Configuration
6.7.3 | Request New Scope or Country/Region Activation via SAP Central Business Configuration | Application Design and Configuration
6.7.4 | Revise Business Roles and Business Catalogs | Technical Architecture & Infrastructure
6.8 | New Scope Item Activation for Manage Your Solution App | Application Design and Configuration
6.8.1 | Review and Request New Scope Activation for Manage Your Solution App | Application Design and Configuration
6.8.2 | Revise Business Roles and Business Catalogs | Technical Architecture & Infrastructure
6.9 | New Country/Region Expansion for Manage Your Solution App | Application Design and Configuration
6.9.1 | Verify Requirements for New Country/Region | Application Design and Configuration
6.9.2 | Set Up Exchange Rates for New Country/Region | Application Design and Configuration
6.9.3 | Extend Solution to Include a New Country/Region for Manage Your Solution App | Application Design and Configuration